## Sheet1
Release No. | Date | Features | Team Release Date
1 | 2017-01-22 | 1. Advance Requisition Entry(Overseas Travel - Executives/HO Employee)
2. Advance Requisition Entry(Local Travel - HO Executives)
3. Advance Requisition Entry(Local Travel - HO Other than Executive Grade)
4. Advance Cash Requisition Entry(Petty)
5. Advance Cash Requisition Entry(Event/Training/Workshop)
10. Vendor Advance Payment Entry
2 | 2017-02-06 | 6. Verify Requested Advance by Line Supervisor, Accounts, Fund Manager | 2017-01-30
7. Advance Approval By CFO/CEO
11. Email Notification to line supervisor regarding advance request
20. Advance issue report by employee
Fix-up on Release 1
3 | 2017-02-13 | 9. Advance Settlement (Refund.Reimbursement) | 2017-01-06
17. Reimbursement of advance from sponsor
20. Advance Settlement report by employee (category wise report)
20. Settled Bill By Category Report
20. Unadjusted advance report by category report
Fix-up on Release 2
4 | 2017-02-20 | Account Configuration for MIS Integration | 2017-02-15
8. Voucher Entry On Final Approval
15. Integrate with Accounts Module in appropriate GL Head
20. Summary Report by Category
Fix-up on Release 3
5 | 2017-02-27 | Advance Aging Report | 2017-02-22
12. Travelling Expense Report (Overseas Executives)
Travelling Expense Report (Local-HO Executives)
13. Travelling Expense Report(HO Other than Executives)
14. Miscellaneous Expense Report (MER)
Fix up Release 4
6 | 2017-03-02 | Fix up Issues and Furnishing Project | 2017-02-27
Final Release
7 | 2017-03-05 | Project On Live
2017-03-01