## Sheet1
Release No. | Date | Features
1 | 2017-01-22 | 1. Advance Requisition Entry(Overseas Travel - Executives/HO Employee)
2. Advance Requisition Entry(Local Travel - HO Executives)
3. Advance Requisition Entry(Local Travel - HO Other than Executive Grade)
4. Advance Cash Requisition Entry(Petty)
5. Advance Cash Requisition Entry(Event/Training/Workshop)
10. Vendor Advance Payment Entry
2 | 2017-02-06 | 6. Verify Requested Advance by Line Supervisor, Accounts, Fund Manager
7. Advance Approval By CFO/CEO
11. Email Notification to line supervisor regarding advance request
20. Advance issue report by employee
Fix-up on Release 1
3 | 2017-02-13 | 9. Advance Settlement (Refund.Reimbursement)
17. Reimbursement of advance from sponsor
20. Advance Settlement report by employee (category wise report)
20. Settled Bill By Category Report
20. Unadjusted advance report by category report
Fix-up on Release 2
4 | 2017-02-20 | Account Configuration for MIS Integration
8. Voucher Entry On Final Approval
15. Integrate with Accounts Module in appropriate GL Head
20. Summary Report by Category
Fix-up on Release 3
5 | 2017-02-27 | Advance Aging Report
12. Travelling Expense Report (Overseas Executives)
Travelling Expense Report (Local-HO Executives)
13. Travelling Expense Report(HO Other than Executives)
14. Miscellaneous Expense Report (MER)
Fix up Release 4
6 | 2017-03-02 | Fix up Issues and Furnishing Project
Final Release
7 | 2017-03-05 | Project On Live